## Sheet1
Event Planning Checklist |  |  |  |  | 2025-06-12 17:15
Task Description | Due Date | Assigned To | Status
Clean-up plan | 2025-06-23 | Everyone | Not Started
Prepare thank-you notes | 2025-06-23 | Rahul Verma | In Progress
Event-day coordination | 2025-06-22 | Dev Mehta | Completed
Set up venue | 2025-06-22 | Aanya Desai | Not Started
Setup photo booth | 2025-06-21 | Meera Iyer | Completed
Arrange games | 2025-06-20 | Neha Agarwal | Completed
Check audio/video system | 2025-06-20 | Arjun Singh | In Progress
Create seating chart | 2025-06-20 | Rohan Gupta | Not Started
Confirm RSVPs | 2025-06-19 | Priya Sharma | Not Started
Arrange catering | 2025-06-18 | Aanya Desai | In Progress | Completed tasks | 8
Order cake | 2025-06-18 | Rahul Verma | In Progress | In progress tasks | 8
Buy return gifts | 2025-06-17 | Neha Agarwal | In Progress | Not started tasks | 3
Set up playlist | 2025-06-17 | Dev Mehta | In Progress
Hire photographer | 2025-06-16 | Arjun Singh | Completed
Send invitations | 2025-06-16 | Rohan Gupta | In Progress
Finalize guest list | 2025-06-15 | Priya Sharma | Completed
Order party supplies | 2025-06-15 | Kriti Jain | Completed
Decor planning | 2025-06-14 | Kriti Jain | Completed
Book venue | 2025-06-13 | Meera Iyer | Completed
Budget review | 2025-06-13 | Meera Iyer | In Progress
This shape represents a table slicer. Table slicers are supported in Excel 2013 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel 2013 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are supported in Excel 2013 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.